# AI-Based NO₂ Mapping Platform: Risk-Hardened Plan (v3)

Revised 18 October 2026 (v3 adds lagged weather and boundary layer height, keeps the 0.05° grid, and re-times the schedule to a realistic 38 working days). Same project as the original plan (0.05° tropospheric NO₂ column mapping, draw-any-polygon live feature, gap reconstruction, uncertainty, honest validation), restructured so that every known risk has an early signal, a counter and a fallback, and so that a working end-to-end version exists by Day 28 even if later stages slip.

## 1. What changed (v2 from the original plan, v3 from v2)

- Delhi vertical slice first. Delhi goes from data to model to live polygon app before any other city is modelled. Bengaluru and Kolkata exports run in the background and are used after the MVP.

- Stage 0 is now a set of go/no-go gates (3 days). Facts the original plan assumed (data versions, weather latency, quota cost, cell definition) are measured before any model work.

- Decisions that remove risk are locked early (section 3), not discovered late.

- Evaluation is split into city-wide daily level and within-city spatial pattern, so a good result cannot hide behind the seasonal cycle and a poor one is not misread.

- Every phase has an exit gate and an explicit fallback. A cut ladder (section 10) says what to drop, in order, if time runs short.

- New risks added from research: processor-version drift, weather-data latency, Earth Engine monthly quotas, satellite outages, retrieval bias and aerosol-as-cloud, and an undefined observed-cell rule.

- v3: lagged weather and boundary layer height (BLH) added. Features now include BLH at the overpass hour and lagged weather (previous-day wind, 24 h and 48 h mean wind, a wind × BLH ventilation proxy, previous-day precipitation), all built from weather only (D4, D8). A Phase 3 ablation checks that they beat run-to-run noise.

- v3: the grid stays at 0.05°; no 1 km grid. TROPOMI’s native pixel is about 5.5 × 3.5 km, so a 1 km grid would repeat one retrieval across many cells and inflate the apparent sample size. Static layers are still sampled at about 1 km and summarised per cell (D8).

- v3: Delhi is the NCR bounding box, not Delhi NCT alone. NCT is only about 50 cells at 0.05°, which makes spatial blocking impractical (risk 8). Stage 0 reports the actual cell count.

- v3: wind-aware emitter exposure moves up to a Should feature. It is the main route by which weather can change the within-city spatial pattern, so it is cut late, not early.

- v3: schedule re-timed. Phase 3 now has 6 days and Phase 4 has 10. MVP is Day 28, Complete Day 32, Stretch Day 35.

Timing: about 38 working days plus 4 buffer days at 5–6 hours a day (roughly 7–8 calendar weeks at five working days a week).

## 2. Scope in three tiers

| Tier | Contents | Target |
| --- | --- | --- |
| Must (MVP) | Delhi pipeline; XGBoost Model A vs baselines under blocked and chronological splits; calibrated intervals; polygon app for any Indian region with data (draw, date, map); cell states observed / insufficient; exports; README with limits | Day 28 |
| Should (Complete) | Bengaluru and Kolkata training; leave-one-city-out transfer; Hyderabad case study; OOD flag verified against held-out error; wind-aware emitter exposure; MLflow tracking | Day 32 |
| Could (Stretch) | Model B gap reconstruction vs IDW and climatology; 7-day composite and nearest-clear-date alternatives; hosted public live demo; population and built-up ablations | Day 35 |

Out of scope: forecasting, ConvLSTM, surface-concentration calibration, a fourth training city, PostGIS, drift or retrain automation, per-request retraining, a 1 km grid, 1 km downscaling claims, coastal modelling (water is masked and coastal cells are warned only).

The target is the TROPOMI-retrieved tropospheric NO₂ column (µmol/m²), not true NO₂. This is stated in code, UI and README.

## 3. Decisions locked in Stage 0 (they remove risk)

D1. Target definition. The model predicts the retrieved product. Accuracy is reported against TROPOMI only. Station data (if accessible) gives correlation and bias, never accuracy.

D2. Observed-cell rule. A 0.05° cell is observed if at least a minimum fraction of its area (initial guess 50%, sensitivity-checked at 30% and 70%) is covered by valid pixels (QA threshold set in Stage 0). Several orbits on one day are combined as a valid-area-weighted mean. Each cell stores n_valid_fraction and sub-pixel spread. Check the native scale of the GEE band before regridding.

D3. Time window and versions. Store the processor and algorithm version of every image in the Parquet files. Plot the monthly mean by version to find step changes. Train on a consistent-version period (start around mid-2022; confirm from the version plot), with a fixed chronological test period and a separate version-shift test on the newest period (after the November 2025 processor update). Do not train on pre-2021 data (known low bias).

D4. One weather source, one date limit. Weather inputs are wind u/v, temperature, humidity, pressure, precipitation and boundary layer height (BLH) at the overpass hour, plus lagged versions (D8). ERA5-Land hourly (via GEE) is the default for everything except BLH, which ERA5-Land does not provide; confirm this in Stage 0 by listing the bands of the GEE ERA5 collections. If BLH is missing, take it from ERA5 single levels (candidate access paths: the Copernicus CDS API, or a cloud copy that supports fast subsetting). CDS requests can queue for minutes to hours, so time the live-request path in Stage 0 and cache BLH if needed. Then run a parity test: if all weather from the ERA5 single-levels source matches the ERA5-Land mix within run-to-run noise, use it for everything so there is one weather source (its preliminary data runs only days behind real time); otherwise keep ERA5-Land plus BLH. Find each source’s actual last available date; the date picker is capped at the earliest of them. Final ERA5-Land runs 2–3 months behind real time; the faster preliminary versions are later overwritten, so using them live while training on final data is a small skew. Match weather to the overpass using the timezone (UTC hour from the cell longitude), with a unit test.

D5. Quota budget. Measure the Earth Engine compute cost of one live request and of the full training export. Choose a noncommercial tier, set a daily limit on the project, and keep a quota log. Use one project only (spreading across projects to bypass limits breaks the terms).

D6. Error taxonomy. Four distinct outcomes, never mixed: observed, reconstructed, insufficient (with reason code: clouds, haze, water, low coverage), and system_error (GEE, OSM, weather or satellite-outage failure; never cached as data). A date with no overpass data gets no_overpass, not insufficient.

D7. Demo setup. Primary demo: local run plus pre-computed cached Delhi and Hyderabad polygons. A hosted public live endpoint is a stretch goal and only if the measured quota cost allows it.

D8. Grid, lags and study area. The grid stays at 0.05° because TROPOMI’s native pixel is about 5.5 × 3.5 km; a 1 km grid would repeat the same retrieval in many cells without adding information. Roads, elevation and emitter distance are computed at about 1 km and summarised per cell as mean, standard deviation and maximum. Lagged weather: previous-day mean wind u/v, 24 h and 48 h mean wind before the overpass, a ventilation proxy (wind speed × BLH) and previous-day precipitation. Lags use weather only, never NO₂, so live requests have the same inputs. The Delhi study area is the NCR bounding box rather than NCT alone; Stage 0 reports its cell count.

## 4. Data sources and their risk notes

| Data | Source | Role | Risk note |
| --- | --- | --- | --- |
| NO₂ column | GEE COPERNICUS/S5P/OFFL/L3_NO2 | Target and observation mask | Use OFFL, not NRTI. Version drift (D3). Collection is current through early October 2026 |
| Cloud fraction | GEE COPERNICUS/S5P/OFFL/L3_CLOUD | Realistic gap masks | Haze can be flagged as cloud, so winter gaps are non-random |
| Weather | GEE ERA5-Land hourly; BLH from ERA5 single levels (D4) | Wind u/v, temperature, humidity, pressure, precipitation and BLH at overpass hour, plus lagged versions | 2–3 month latency (D4); no BLH in ERA5-Land (confirm); check coastal coverage |
| Elevation | GEE SRTM | Mean and standard deviation per cell | Low risk |
| Roads | OSM via osmnx/Overpass, cached per region | Road density, major roads weighted higher | Uneven coverage; warn on unusually low density |
| Emitters | One public power-plant list plus an industrial list if reliable | Distance and wind-aware exposure (Should) | Check list date and counts per city; flag near-constant feature |
| Water fraction | GEE ESA WorldCover or JRC water | Mask only (land / mixed / water) | Cutoffs 20% and 80% are guesses; sensitivity check |
| Stations | CPCB, optional | Correlation and bias only | Drop if access is manual |
| India boundary | Survey of India or officially aligned source | Clipping and validation | Use one fixed version, recorded in metadata |

Training data is a one-time batch export by city and month to Parquet. Live requests call GEE only for the selected area and date.

## 5. Timeline with gates and fallbacks

### Phase 0: Feasibility gates (Days 1–3)

- Repo, environment, GEE project registered, tier chosen, configs.

- Pull one month of Delhi NO₂. Inspect units, QA flags, valid fraction, regridding scale and what the collection already filters.

- Version plot (D3). Weather latency, BLH source and live-access speed, and coastal check (D4). Quota measurement (D5).

- Write the cell-ID scheme, grid and observed-cell rule (D2). Fix the NCR bounding box and report its cell count (D8). Compute the water mask.

- Confirm CPCB access (drop if manual). Pick emitter datasets and note limits.

- Decide local vs hosted demo (D7).

Gate G0 (Day 3): one month of Delhi in Parquet with metadata, plus a one-page feasibility note answering every check above. If it fails: if valid-pixel fraction is too low for daily cells, switch the target to weekly composites (keep the daily path as a Could). If quota cost is too high, shrink the training export (fewer months, coarser sampling) before changing anything else.

### Phase 1: Delhi data pipeline (Days 4–8)

- Resumable, batched export by month with retries and backoff; a manifest records which months are done.

- Weather (including lags and BLH) matched to the overpass; static layers sampled once and cached; road density and elevation computed over the land part of each cell.

- Quality filter with a separate observation mask; invalid pixels never become values.

- Report valid-pixel fraction by month and season.

- Start the Bengaluru and Kolkata exports in the background as soon as Delhi works (off-peak, in small batches). They are used from Phase 5.

Gate G1 (Day 8): Delhi complete for the chosen window; manifest has no missing months; data dictionary draft. If it fails: shorten the Delhi window to 2 years; skip months that fail twice and record them.

### Phase 2: Features and baselines (Days 9–12)

- One shared feature module used by training and live inference; feature schema versioned.

- Features: weather at the overpass hour (wind as u/v or circular, temperature, humidity, pressure, precipitation, BLH), lagged weather and ventilation proxy (D8), month encodings, distance to major emitters, road density, elevation mean and standard deviation. Wind-aware emitter exposure (upwind, emitter-weighted distance from the overpass-hour wind) is built here. No lat/lon in transfer experiments. Check the static-feature correlation matrix.

- Compute the residual autocorrelation range (variogram) to set spatial block size.

- Baselines: per-cell monthly climatology (training years only), static-only model, Ridge, daily city mean (spatial mean).

Gate G2 (Day 12): baselines scored under the evaluation protocol (section 6); block size chosen. If the block size is larger than about half of Delhi: Delhi uses chronological validation plus coarse blocks with buffer. The spatial-generalization claim then rests on leave-one-city-out only.

### Phase 3: Model A, uncertainty, validation (Days 13–18)

- Log-transformed target; XGBoost hist with limited threads.

- Feature ablation: weather only (overpass hour), plus lags and BLH, plus static, plus temporal. Population and built-up fraction are kept only if they beat run-to-run noise on blocked splits.

- Metrics (MAE, RMSE, R², bias) in µmol/m², daily, weekly and monthly, by season, and as defined in section 6.

- Split-conformal intervals (section 7), OOD flag, MLflow logging.

Gate G3 (Day 18, MVP model checkpoint): Model A beats per-cell climatology on blocked and chronological splits by more than seed-to-seed noise, or the result is reported honestly as it stands. If it does not beat climatology: report skill on anomalies; check the static-only baseline. Keep the app (Phase 4) as a mapping tool that returns observed values plus climatology-anchored estimates, clearly labelled. Do not tune on the test period.

### Phase 4: Live polygon app (Days 19–28)

- FastAPI job flow: POST /api/jobs, GET /api/jobs/{id}, GET /api/results/{id}, GET /api/models. File-based job store.

- Polygon validation (self-intersection, vertex count, India clipping, size limit tied to the quota measurement) and per-IP rate limiting.

- Compute on the bounding box plus a 2–3 cell buffer; return only cells inside the polygon. A polygon smaller than one cell returns that cell with a resolution warning. Edge cells keep an overlap fraction that weights the summary.

- Cell states per D6. Until Phase 6 sets thresholds, Model A fills missing cells.

- Cache keyed on cell ID, date, feature version, processor version and model version.

- Date picker capped by D4. A "data as of" line shows the latest available date and processor versions.

- Leaflet frontend: observed / reconstructed / insufficient layers, coverage and uncertainty layers, cell inspector, summary panel, exports (GeoTIFF with nodata, CSV with status column).

- Demo mode: pre-computed Delhi and Hyderabad polygons.

- Parity test: same polygon and date through training and live paths gives identical features, including clipping, lags and BLH.

Gate G4 (Day 28, MVP complete): a map from a drawn polygon without retraining, with units, coverage, model version, data versions and warnings; exports work. If it runs long: drop GeoTIFF export (keep CSV), drop the uncertainty layer to an interval column, keep demo mode.

### Phase 5: Multi-city training and transfer (Days 29–32)

- Add Bengaluru and Kolkata (exports already running). Verify per-city valid fractions and emitter counts.

- One or two leave-one-city-out runs, then the untouched Hyderabad case study (data pulled only now, never used for tuning).

- Check the OOD flag: flagged cells must show higher held-out error. Check interval coverage in each held-out city.

- Poor transfer is reported, not tuned away.

Gate G5 (Day 32, Complete tier): transfer table and OOD evidence written up. If Kolkata is not ready: train on Delhi and Bengaluru, and use Kolkata and Hyderabad as test cities.

### Phase 6: Gap reconstruction, time-boxed (Days 33–35)

- Model B uses same-day neighbour means, nearest valid values on earlier dates, monthly climatology and distance to the nearest valid cell. Train with random masking so context never contains the target; randomly drop temporal context so live requests with no later data still work.

- Evaluate on hidden valid cells only: random pixels and contiguous gaps separately, plus real gap shapes copied from other dates (including winter-haze shapes), against IDW, temporal interpolation and climatology.

- Set insufficient-data thresholds (gap fraction, distance to nearest valid cell) where reconstruction stops beating climatology. Return nodata plus reason code, and offer labelled alternatives (nearest clear date, 7-day composite, monthly climatology).

- Widen intervals with distance to the nearest valid cell.

Gate G6 (Day 35): Model B beats IDW and climatology on contiguous gaps by more than seed noise. If not (or if time runs out): ship Model A plus the insufficient-data rule and report the comparison as a result. Day 33 is a go/no-go: if the first quick comparison shows no headroom, stop and move on.

### Phase 7: Polish (Days 36–38)

- Tests for acquisition, grid and feature parity; fixtures that replay a failed GEE call.

- README: provenance, versions used, limitations (column vs surface, retrieval bias, clear-sky bias of the reconstruction test, haze gaps, coastal caveat), setup.

- MLflow summary and a one-page retraining note.

- Screenshots, a short walkthrough, final demo mode.

### Buffer (Days 39–42)

For GEE or quota trouble, a failed ablation, or a stage that ran long. Unused buffer goes to the README and demo.

## 6. Evaluation protocol (honest by construction)

- Splits: spatial blocks larger than the autocorrelation range with a buffer gap; a chronological split; leave-one-city-out; a version-shift test on the newest period. No random splitting of neighbouring cells to claim spatial generalization.

- Two-level scoring: (a) the daily city-mean level (does the model capture the seasonal and weather-driven level?) and (b) within-city spatial pattern per day (spatial correlation and error after removing that day's city mean). A model that only learns the seasonal cycle will pass (a) and fail (b).

- Baselines always shown: per-cell climatology, static-only, Ridge, daily city mean.

- Aggregation: daily, weekly and monthly, since single-day retrievals are noisy; stratified by season, with winter haze reported separately.

- Rules: no future-derived features; tune only on training and validation; Hyderabad untouched; never show a confidence percentage without a defined, evaluated meaning.

- Reproducibility: fix seeds, report run-to-run spread over at least 3 seeds, and call a gain real only if it exceeds that spread.

## 7. Uncertainty and OOD

- Intervals: split-conformal residual quantiles calibrated on spatial-block validation, stratified by season and by distance to the nearest valid cell. Report coverage and width on blocked, chronological, version-shift and held-out-city sets. If coverage drops in a new city, widen with the OOD score and say so.

- OOD flag: standardized feature distance from training data. Accept it only if flagged cells show higher held-out error.

- Label rules: the UI shows intervals as intervals with their nominal level and the evaluated coverage, nothing else.

## 8. Reliability design for the live feature

- Quota protection: cell-level cache, per-IP rate limit, polygon size cap, daily project limit, quota log, demo mode as fallback.

- Failure handling: retries with backoff; system_error and no_overpass never cached as data; a clear message tells the user which one occurred.

- Version safety: cache keys include processor version; metadata panel lists data and model versions; a startup check warns if the newest images use a processor version not seen in training.

- Clipping and parity: one shared feature module; parity test in CI.

## 9. Risk register

| # | Risk | Early signal | Counter | Fallback | Stage |
| --- | --- | --- | --- | --- | --- |
| 1 | Processor-version drift in NO₂ product | Step change in monthly means by version | Store versions; consistent training window; version-shift test | Report shift; restrict to one version period | 0, 3, 5 |
| 2 | Weather latency limits dates | Latest ERA5-Land date months behind | Cap date picker; one source; parity test before adding another | Use only dates with all inputs | 0, 4 |
| 3 | GEE monthly quota exhausted | Slow jobs, quota log near limit | Measure cost; batch export once; cache; rate limit; daily limit | Demo mode; local run | 0, 4, 7 |
| 4 | Satellite or GEE outage | Missing orbits, job errors | OFFL only; system_error and no_overpass codes; no caching of failures | Pre-computed demo | 1, 4 |
| 5 | Retrieval bias and aerosol flagged as cloud | Winter-haze gaps cluster by season | Label as TROPOMI-retrieved; season-stratified metrics; haze evaluated separately | README limits; no ground-truth accuracy claims | 3, 7 |
| 6 | Observed cell undefined or unstable | Results change with the valid-fraction threshold | Rule D2 with sensitivity check | Use the most conservative threshold | 0, 2 |
| 7 | Model cannot beat climatology | G3 comparison | Anomaly skill; static-only baseline; two-level scoring | Report honestly; label estimates as climatology-anchored | 2, 3 |
| 8 | Spatial blocks too large for Delhi | Variogram range > half of city | NCR bounding box for more cells; chronological plus coarse blocks; leave-one-city-out for spatial claim | State the limit in README | 2 |
| 9 | Interval under-coverage in new cities | Coverage far below nominal in Hyderabad | Conformal calibration; OOD widening; report per-city coverage | Show intervals only where evaluated | 3, 5 |
| 10 | Training-serving skew | Parity test fails | Shared feature module; versioned schema; dropped temporal context in Model B | Block release until parity passes | 2, 4 |
| 11 | Poor transfer to new cities | Large leave-one-city-out error | OOD flag; no lat/lon; report as found | Warn and state not validated | 5 |
| 12 | Reconstruction looks better than reality | Large gap between random and real-shape gaps | Real gap shapes copied onto clear days; say so | Ship Model A plus insufficient rule | 6 |
| 13 | Thin or stale emitter list | Few emitters per city; near-constant feature | Count per city; flag; use plain distance | Drop the feature for that city | 1, 2 |
| 14 | Uneven OSM coverage | Road density unusually low | Warning in UI; document dependence | Elevation-only static set | 1, 4 |
| 15 | Coastal and water cells | Mixed cells in output | Water mask; reason code "water"; coastal warning | Land-only prediction | 4 |
| 16 | Noisy daily retrievals | Poor daily, good weekly scores | Report weekly and monthly aggregates | Weekly composite target | 3 |
| 17 | XGBoost cannot extrapolate | Out-of-range inputs | Log target; OOD warning | Refuse out-of-range requests | 3, 4 |
| 18 | Column vs surface confusion | Users read output as ground-level NO₂ | Units and "column" label in schema, UI, README | None needed | All |
| 19 | Schedule slip | A gate missed by more than 1 day | Gates, time-boxes, cut ladder, buffer | Section 10 | All |
| 20 | Scope creep | Work not in the phase list | Freeze features before Day 13; no new modules before MVP gates | Park in future work | All |
| 21 | BLH unavailable or too slow for live requests | No BLH in GEE bands; slow queue in the Stage 0 timing test | Fast-subset source or cached BLH; BLH and lags in the parity test | Drop BLH, keep lagged wind; report the ablation | 0, 4 |
| 22 | Lags and BLH add no skill | Ablation gain within seed noise | Ablation in Phase 3; keep only features that beat run-to-run noise | Drop them; keep the simpler feature set | 3 |

## 10. Cut ladder (drop in this order if behind)

- Model B context features (keep Model A plus insufficient-data rule).

- Population and built-up ablations.

- GeoTIFF export (keep CSV).

- Kolkata (train on Delhi and Bengaluru; test on Kolkata and Hyderabad).

- Hosted public live endpoint (local run plus demo mode).

- Wind-aware emitter exposure (keep plain emitter distance).

- Hyderabad case study replaced by a held-out city already in the data.

Never cut: the evaluation protocol, the parity test, the system_error / insufficient separation, or the README limits.

## 11. Definition of done

MVP (Day 28): the Delhi batch pipeline runs; Model A is trained, saved and compared with baselines under blocked and chronological splits; a user can draw a polygon and get a map without retraining; results show units, coverage, model version, data versions and warnings; exports work; the README documents provenance and limits.

Complete (Day 32+): multi-city training, transfer results including Hyderabad, calibrated intervals with a verified OOD flag, MLflow-tracked model versions. Stretch: gap reconstruction evaluated on masked observations.

Resume evidence (measured only): MAE and RMSE vs climatology, gain from lagged weather and BLH, within-city spatial correlation, spatial vs random split gap, version-shift result, transfer metrics, interval coverage, reconstruction error vs IDW, training time, peak memory, inference latency, and cache hit rate.

## 12. Future work

Coastal modelling (add a coastal city, ports and shipping emitters, distance to coast once coastal training data exists, separate coastal evaluation, re-tuned water cutoffs); retraining when the full-mission reprocessing lands; weekly composite product; PM2.5 or surface-level calibration if station access becomes automatic.